## Tasks
Task ID | Task Name | Bucket Name | Progress | Priority | Assigned To | Created By | Start date | Due date | Is Recurring | Late | Completed Date | Completed By | Completed Checklist Items | Checklist Items | Labels | Description
DXa11TmTykyMrRiQROeZlMkADngi | Conduct testing | Testing | Completed | Important |  | Sooriyaarachchi M.D.A. it21173790 |  |  | false | false | 05/29/2025 | Sooriyaarachchi M.D.A. it21173790 |  |  | Blue
7nDvOaIc5kqKjWQL4cUfAckAJQ9G | Conduct user testing | Design | Completed | Important |  | Sooriyaarachchi M.D.A. it21173790 |  |  | false | false | 05/29/2025 | Sooriyaarachchi M.D.A. it21173790 |  |  | Yellow
LmC1loGiAkuQ-wvJPA9kd8kADnqe | Develop code | Development | Completed | Medium |  | Sooriyaarachchi M.D.A. it21173790 |  |  | false | false | 05/29/2025 | Sooriyaarachchi M.D.A. it21173790 |  |  | Green
rT_49U8zJEiS7aL-cb48KskAANfG | Draft preliminary software specifications | Analysis/Software requirements | Completed | Medium |  | Sooriyaarachchi M.D.A. it21173790 |  |  | false | false | 05/29/2025 | Sooriyaarachchi M.D.A. it21173790 |  |  | Pink
-Va-fj4mOkuGfRQrG5Z4s8kAK16V | Determine project scope | Scope | Completed | Medium |  | Sooriyaarachchi M.D.A. it21173790 |  |  | false | false | 05/29/2025 | Sooriyaarachchi M.D.A. it21173790 | 2/2 | Define potential obstacles;Define goals | Pink
2aTGNxwHg0-42YKaGMYWj8kAKfDY | Develop prototype based on specifications | Development | Completed | Medium |  | Sooriyaarachchi M.D.A. it21173790 |  |  | false | false | 05/29/2025 | Sooriyaarachchi M.D.A. it21173790 |  |  | Yellow
w0mYn1Y520WNyxjRUvF8UMkAAXVs | Conduct needs analysis | Analysis/Software requirements | Completed | Medium |  | Sooriyaarachchi M.D.A. it21173790 |  |  | false | false | 05/29/2025 | Sooriyaarachchi M.D.A. it21173790 | 0/3 | Evaluate information;Collect information;Prepare for data gathering | Pink
knVGSoi35EmAz7yD-r55JMkAOCll | Project Initiation | Analysis/Software requirements | Completed | Important | Kumarathunga S.A.D.S it21118340;Senanayake W.G.B. it21158322;Ranaweera A.P. it21182396 | Sooriyaarachchi M.D.A. it21173790 | 2024-08-10 | 08/16/2024 | false | false | 05/29/2025 | Sooriyaarachchi M.D.A. it21173790 | 4/4 | Assign project roles & responsibilities;Set up GitHub/Drive repo for files;Schedule weekly review meetings;Define project objectives | Pink
8aUnIeFG3kWXbjtry46ka8kAMb2l | Web Interface Development | Design | Completed | Urgent | Kumarathunga S.A.D.S it21118340;Senanayake W.G.B. it21158322;Ranaweera A.P. it21182396 | Sooriyaarachchi M.D.A. it21173790 | 11/01/2024 | 03/18/2025 | false | false | 05/29/2025 | Sooriyaarachchi M.D.A. it21173790 | 4/4 | Connect front-end to backend model;Design a front-end;Create text input/upload functionality;Display prediction results and confidence levels
A_GGXBPwaESjkCgqhPXL5skAGEaw | Conduct Needs Analysis | Analysis/Software requirements | Completed | Medium | Kumarathunga S.A.D.S it21118340;Ranaweera A.P. it21182396;Senanayake W.G.B. it21158322 | Sooriyaarachchi M.D.A. it21173790 |  | 08/31/2024 | false | false | 05/29/2025 | Sooriyaarachchi M.D.A. it21173790
nOytKaMgT0C2Ev81VHZGUskAEHMn | Collect Functional Requirements | Analysis/Software requirements | Completed | Medium | Kumarathunga S.A.D.S it21118340;Ranaweera A.P. it21182396;Senanayake W.G.B. it21158322 | Sooriyaarachchi M.D.A. it21173790 |  | 09/30/2024 | false | false | 05/29/2025 | Sooriyaarachchi M.D.A. it21173790
4YDMmmaM3kOwbbk7fqU7j8kAJ5yv | Collect Non-Functional Requirements | Analysis/Software requirements | Completed | Medium | Kumarathunga S.A.D.S it21118340;Ranaweera A.P. it21182396;Senanayake W.G.B. it21158322 | Sooriyaarachchi M.D.A. it21173790 |  | 08/31/2024 | false | false | 05/29/2025 | Sooriyaarachchi M.D.A. it21173790
OulnUHlGi0-dATzpTm9NMMkAJJbc | Identify Stakeholders | Analysis/Software requirements | Completed | Medium | Kumarathunga S.A.D.S it21118340;Ranaweera A.P. it21182396;Senanayake W.G.B. it21158322 | Sooriyaarachchi M.D.A. it21173790 |  | 08/31/2024 | false | false | 05/29/2025 | Sooriyaarachchi M.D.A. it21173790
pXRJ8EQTikW59ycjkkK1wckANuOv | Finalize Software Requirements Specification(Project Proposal) (SRS) | Analysis/Software requirements | Completed | Medium | Kumarathunga S.A.D.S it21118340;Ranaweera A.P. it21182396;Senanayake W.G.B. it21158322 | Sooriyaarachchi M.D.A. it21173790 |  | 08/23/2024 | false | false | 05/29/2025 | Sooriyaarachchi M.D.A. it21173790
KSM0nQZArUuKGCi5qpyNackABw-- | Define Project Scope | Scope | Completed | Medium | Kumarathunga S.A.D.S it21118340;Ranaweera A.P. it21182396;Senanayake W.G.B. it21158322 | Sooriyaarachchi M.D.A. it21173790 |  | 09/30/2024 | false | false | 05/29/2025 | Sooriyaarachchi M.D.A. it21173790
tIqSHtg8hUKNGMZWiKoYMskAEohi | List Assumptions and Constraints | Scope | Completed | Medium | Kumarathunga S.A.D.S it21118340;Ranaweera A.P. it21182396;Senanayake W.G.B. it21158322 | Sooriyaarachchi M.D.A. it21173790 |  | 09/30/2024 | false | false | 05/29/2025 | Sooriyaarachchi M.D.A. it21173790
oxvhJySW-E610rLSC6A-TskACsAI | Set Deliverables | Scope | Completed | Medium | Kumarathunga S.A.D.S it21118340;Ranaweera A.P. it21182396;Senanayake W.G.B. it21158322 | Sooriyaarachchi M.D.A. it21173790 |  | 10/01/2024 | false | false | 05/29/2025 | Sooriyaarachchi M.D.A. it21173790
3AuVQDnkiE6IpyvYfH-Ya8kAAgdU | Define Success Criteria | Scope | Completed | Medium | Kumarathunga S.A.D.S it21118340;Ranaweera A.P. it21182396;Senanayake W.G.B. it21158322 | Sooriyaarachchi M.D.A. it21173790 |  | 11/01/2024 | false | false | 05/29/2025 | Sooriyaarachchi M.D.A. it21173790
HqgUhrnOxUa2Day8-vykG8kALUfM | System Architecture Design | Design | Completed | Medium | Kumarathunga S.A.D.S it21118340;Ranaweera A.P. it21182396;Senanayake W.G.B. it21158322 | Sooriyaarachchi M.D.A. it21173790 |  | 11/09/2024 | false | false | 05/29/2025 | Sooriyaarachchi M.D.A. it21173790
AdY-pzTC-EmqP3PMnKvk7ckAPUkN | Feature Engineering Plan | Design | Completed | Medium |  | Sooriyaarachchi M.D.A. it21173790 |  |  | false | false | 05/29/2025 | Sooriyaarachchi M.D.A. it21173790
kkay7dCd2ECqN-E_ruHjiMkAOrDX | User Interface Mockups | Design | Completed | Medium | Kumarathunga S.A.D.S it21118340;Ranaweera A.P. it21182396;Senanayake W.G.B. it21158322 | Sooriyaarachchi M.D.A. it21173790 |  | 11/30/2024 | false | false | 05/29/2025 | Sooriyaarachchi M.D.A. it21173790
uu9OsiOXU0mUDCTBYJigH8kAH9WT | Conduct User Testing | Design | Completed | Medium | Kumarathunga S.A.D.S it21118340;Ranaweera A.P. it21182396;Senanayake W.G.B. it21158322 | Sooriyaarachchi M.D.A. it21173790 |  | 12/01/2024 | false | false | 05/29/2025 | Sooriyaarachchi M.D.A. it21173790
imFOzCboXkKdngT-Xu8AnskAM0hy | Data Collection and Cleaning | Development | Completed | Medium | Kumarathunga S.A.D.S it21118340;Ranaweera A.P. it21182396;Senanayake W.G.B. it21158322 | Sooriyaarachchi M.D.A. it21173790 |  | 12/01/2024 | false | false | 05/29/2025 | Sooriyaarachchi M.D.A. it21173790
uEE0p5mHTk-r1cSi6_mqDMkAMNRZ | Implementation backend | Development | Completed | Medium | Kumarathunga S.A.D.S it21118340;Ranaweera A.P. it21182396;Senanayake W.G.B. it21158322 | Sooriyaarachchi M.D.A. it21173790 |  | 12/01/2024 | false | false | 05/29/2025 | Sooriyaarachchi M.D.A. it21173790
tXJ3pBgG10aqfrx8X5zfTMkAMfV_ | Model Training | Development | Completed | Medium |  | Sooriyaarachchi M.D.A. it21173790 |  |  | false | false | 05/29/2025 | Sooriyaarachchi M.D.A. it21173790
-oKRP7J4LkuASg2WeIJ9wckAAiAo | Inference System | Development | Completed | Medium |  | Sooriyaarachchi M.D.A. it21173790 |  |  | false | false | 05/29/2025 | Sooriyaarachchi M.D.A. it21173790
VCOmJ9E6KU-K37vPMTP_9MkAL-L6 | Web Interface Development | Development | Completed | Medium | Kumarathunga S.A.D.S it21118340;Ranaweera A.P. it21182396;Senanayake W.G.B. it21158322 | Sooriyaarachchi M.D.A. it21173790 |  | 03/01/2025 | false | false | 05/29/2025 | Sooriyaarachchi M.D.A. it21173790
UcI7f-6cuU2t5MXeLVXeO8kAPkiM | Unit Testing of Functions | Testing | Completed | Medium | Kumarathunga S.A.D.S it21118340;Ranaweera A.P. it21182396;Senanayake W.G.B. it21158322 | Sooriyaarachchi M.D.A. it21173790 |  | 12/31/2024 | false | false | 05/29/2025 | Sooriyaarachchi M.D.A. it21173790
d7zD-vFnpEiWuIOtJ7gW7skADlfS | Model Accuracy Validation | Testing | Completed | Medium | Kumarathunga S.A.D.S it21118340;Ranaweera A.P. it21182396;Senanayake W.G.B. it21158322 | Sooriyaarachchi M.D.A. it21173790 |  | 12/31/2024 | false | false | 05/29/2025 | Sooriyaarachchi M.D.A. it21173790
XfwANUy8qkSEkrTDSno7k8kABi08 | Feedback Quality Check | Testing | Completed | Medium | Kumarathunga S.A.D.S it21118340;Ranaweera A.P. it21182396;Senanayake W.G.B. it21158322 | Sooriyaarachchi M.D.A. it21173790 |  | 01/01/2025 | false | false | 05/29/2025 | Sooriyaarachchi M.D.A. it21173790
Ef-SsoLJ1UK_R8zpPwXREckAEVkZ | Bug Fixing & Optimization | Testing | Completed | Medium | Kumarathunga S.A.D.S it21118340;Ranaweera A.P. it21182396;Senanayake W.G.B. it21158322 | Sooriyaarachchi M.D.A. it21173790 |  | 01/31/2025 | false | false | 05/29/2025 | Sooriyaarachchi M.D.A. it21173790
y2rKumVrzk6MT3wM8N410MkAE1AA | Write Code Comments and Docstrings | Documentation | Completed | Medium |  | Sooriyaarachchi M.D.A. it21173790 |  | 02/28/2025 | false | false | 05/29/2025 | Sooriyaarachchi M.D.A. it21173790
v2rI8fdtLUiKjoIo2H8ZzckAEmvT | Prepare Final Report | Documentation | Completed | Medium | Kumarathunga S.A.D.S it21118340;Ranaweera A.P. it21182396;Senanayake W.G.B. it21158322 | Sooriyaarachchi M.D.A. it21173790 |  | 04/11/2025 | false | false | 05/29/2025 | Sooriyaarachchi M.D.A. it21173790
RD2POGEiyUyQcU4nvTceQ8kAM2tr | Create User Guide | Documentation | Completed | Medium | Kumarathunga S.A.D.S it21118340;Ranaweera A.P. it21182396;Senanayake W.G.B. it21158322 | Sooriyaarachchi M.D.A. it21173790 |  | 05/18/2025 | false | false | 05/29/2025 | Sooriyaarachchi M.D.A. it21173790
LuCEjU4MCk60AEitGgo3wckAKTkC | Design PowerPoint Slides For PP1 | Presentation | Completed | Medium | Kumarathunga S.A.D.S it21118340;Ranaweera A.P. it21182396;Senanayake W.G.B. it21158322 | Sooriyaarachchi M.D.A. it21173790 |  | 12/01/2024 | false | false | 05/29/2025 | Sooriyaarachchi M.D.A. it21173790
6br1VQyloUimlXPusN-r2MkALpvQ | Practice Viva Q&A for pp1 | Presentation | Completed | Medium | Kumarathunga S.A.D.S it21118340;Ranaweera A.P. it21182396;Senanayake W.G.B. it21158322 | Sooriyaarachchi M.D.A. it21173790 |  | 12/01/2024 | false | false | 05/29/2025 | Sooriyaarachchi M.D.A. it21173790
4QzOMonoV0Ch-9M4cI2APckADfEO | Frontend Development Tasks | Development | Completed | Medium | Kumarathunga S.A.D.S it21118340;Ranaweera A.P. it21182396;Senanayake W.G.B. it21158322 | Sooriyaarachchi M.D.A. it21173790 |  | 03/01/2025 | false | false | 05/29/2025 | Sooriyaarachchi M.D.A. it21173790 | 10/10 | Form validations and user input handling;State management (if using Redux, Zustand, etc.);Responsive design implementation (mobile/tablet/desktop);Connect frontend to backend APIs;Frontend error handling & user feedback messages;Implement UI components (header, footer, navbar, etc.);Implement authentication UI (login/signup);Integrate pages based on wireframes and Figma prototype; Set up frontend environment (React + Vite);Frontend testing (unit, integration, E2E as needed)
Bp2vriQSoEGaWeyZYt7PqskALkgg | Backend Development Tasks (for each microservice) | Development | Completed | Medium | Kumarathunga S.A.D.S it21118340;Ranaweera A.P. it21182396;Senanayake W.G.B. it21158322 | Sooriyaarachchi M.D.A. it21173790 |  | 02/28/2025 | false | false | 05/29/2025 | Sooriyaarachchi M.D.A. it21173790 | 8/8 | Develop RESTful APIs;Middleware (authentication, logging, error handling); Set up backend project structure;Swagger documentation for each service;Service-to-service communication setup; Design and implement database schema;Unit & integration tests;API input validation (e.g., Joi, express-validator)
dnJP_-9MI0m76jYERFJYtckALjWa | CI/CD and DevOps Tasks | Development | Completed | Important | Kumarathunga S.A.D.S it21118340;Ranaweera A.P. it21182396;Senanayake W.G.B. it21158322 | Sooriyaarachchi M.D.A. it21173790 |  | 05/18/2025 | false | false | 05/29/2025 | Sooriyaarachchi M.D.A. it21173790 | 10/10 | Logging and monitoring setup (e.g., CloudWatch);Write Dockerfiles for each microservice;Push Docker images to AWS ECR;Setup AWS ECS Cluster;Environment variables management (AWS Secrets Manager or SSM);Set up GitHub Actions / GitLab CI for automated builds;Create ECS Task Definitions and Services;CI/CD and DevOps Tasks;Create docker-compose setup for local development;Configure automatic deployments on code push
-yaNBIHXuUKr4ITNx_qbDskAPRcd | Integration Tasks | Development | Completed | Important | Kumarathunga S.A.D.S it21118340;Ranaweera A.P. it21182396;Senanayake W.G.B. it21158322 | Sooriyaarachchi M.D.A. it21173790 |  | 03/31/2025 | false | false | 05/29/2025 | Sooriyaarachchi M.D.A. it21173790 | 5/5 | Configure CORS and API Gateway;Integration testing across services;Authentication & Authorization integration (JWT/session);Frontend to API endpoint mapping and testing;Integrate all microservices with frontend
SkN1oYK61U6kIfGe2VvezckABBt- | Testing & QA | Testing | Completed | Important | Kumarathunga S.A.D.S it21118340;Ranaweera A.P. it21182396;Senanayake W.G.B. it21158322 | Sooriyaarachchi M.D.A. it21173790 |  | 03/31/2025 | false | false | 05/29/2025 | Sooriyaarachchi M.D.A. it21173790 | 7/7 | Performance testing;Write unit tests (frontend and backend);Conduct UAT (User Acceptance Testing);Perform integration tests;Manual UI testing;Cross-browser compatibility checks;Bug fixing & retesting
MKaycPQ-8kG7UqNgHmBNzMkAGzWy | Deployment Tasks | Deployment | Completed | Important | Kumarathunga S.A.D.S it21118340;Ranaweera A.P. it21182396;Senanayake W.G.B. it21158322 | Sooriyaarachchi M.D.A. it21173790 |  | 05/18/2025 | false | false | 05/29/2025 | Sooriyaarachchi M.D.A. it21173790 | 4/4 | Deploy frontend to Netlify;Test production environment;Deploy backend to AWS ECS;Perform smoke testing post-deployment
LAEmIHkl6k2LBzGW_VlXuckAOI5j | Create Deployment Report | Documentation | Completed | Medium |  | Sooriyaarachchi M.D.A. it21173790 |  |  | false | false | 05/29/2025 | Sooriyaarachchi M.D.A. it21173790
Apx-JVLWt0-cqoVPQmtq4ckALNF- | Create UI UX report And Video | Documentation | Completed | Medium | Kumarathunga S.A.D.S it21118340;Ranaweera A.P. it21182396;Senanayake W.G.B. it21158322 | Sooriyaarachchi M.D.A. it21173790 |  |  | false | false | 05/29/2025 | Sooriyaarachchi M.D.A. it21173790
v5TBY3e9-kmJLPDDUucHh8kAH2dP | Design PowerPoint Slides for pp2 | Presentation | Completed | Medium | Kumarathunga S.A.D.S it21118340;Ranaweera A.P. it21182396;Senanayake W.G.B. it21158322 | Sooriyaarachchi M.D.A. it21173790 |  | 03/18/2025 | false | false | 05/29/2025 | Sooriyaarachchi M.D.A. it21173790
nIOxESpiJ0GRYFmCr3a7EskAP1TE | Practice Viva Q&A for pp2 | Presentation | Completed | Medium | Kumarathunga S.A.D.S it21118340;Ranaweera A.P. it21182396;Senanayake W.G.B. it21158322 | Sooriyaarachchi M.D.A. it21173790 |  | 03/18/2025 | false | false | 05/29/2025 | Sooriyaarachchi M.D.A. it21173790
uqJa6quoHU6IOSWc99jqeckAAnlT | Design PowerPoint Slides for Final | Presentation | Completed | Medium | Kumarathunga S.A.D.S it21118340;Ranaweera A.P. it21182396;Senanayake W.G.B. it21158322 | Sooriyaarachchi M.D.A. it21173790 |  | 05/24/2025 | false | false | 05/29/2025 | Sooriyaarachchi M.D.A. it21173790
oXXkkyzTYka1NN9sKiWJ28kAA2gY | Practice Viva Q&A for final | Presentation | Completed | Medium | Kumarathunga S.A.D.S it21118340;Ranaweera A.P. it21182396;Senanayake W.G.B. it21158322 | Sooriyaarachchi M.D.A. it21173790 |  | 05/25/2025 | false | false | 05/29/2025 | Sooriyaarachchi M.D.A. it21173790
uSrXlw_0i0umP4E2SfY9IskAFxIH | Design PowerPoint Slides For Proposal Presentition | Presentation | Completed | Medium | Kumarathunga S.A.D.S it21118340;Ranaweera A.P. it21182396;Senanayake W.G.B. it21158322 | Sooriyaarachchi M.D.A. it21173790 |  | 08/04/2024 | false | false | 05/29/2025 | Sooriyaarachchi M.D.A. it21173790
0IJ7jYhptkqU4XAY1sbmYckABOCz | Create Proposal report | Documentation | Completed | Medium | Kumarathunga S.A.D.S it21118340;Ranaweera A.P. it21182396;Senanayake W.G.B. it21158322 | Sooriyaarachchi M.D.A. it21173790 |  | 08/20/2024 | false | false | 05/29/2025 | Sooriyaarachchi M.D.A. it21173790

## Plan name
Plan name | Readify Team- AI-enabled-Intelligent-Assistant-to-Improve-Reading-and-Comprehension-Skills-in-English-RP24-25J-027
Plan ID | 8hUOuoiDmEK119l_Uel5q8kACVsa
Date of export | 05/29/2025